## Sheet1
RYE Scholarship Program Planning Schedule | [20 empty] | Sept. 10, 2017
| Task | Person in Charge | Timing
|  |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
1 | Send/Drop-off RYE Flyers/Post Cards at D6690 High School Guidance Offices | Chair --> Local Volunteers | bar: Timing Mar to Timing May
2 | Committee/Club YEO - Present RYE Program at Local Schools to Recruit Outbounds | YEO / Presenters | bar: Timing Mar to Timing May
3 | Direct Prospective Students to Fill Out Pre-Application Online | Chair --> Students | bar: Timing Mar to Timing Sep
4 | Send Reminder/Invitation via Email to All Prospects to Attend August K/O Weekend | Chair --> Parents & Students | bar: Timing Jul to Timing Aug
5 | Email ROTEX to Recruit Help for Weekends and December Interviews | Chair --> ROTEX | bar: Timing Jul to Timing Aug
6 | AUGUST WEEKEND - Presentation to Parents | Chair --> Parents | bar: Timing Aug
7 | Encourage Prospects to Fill Out Full Application Early (remind Sept/October/November) | Chair --> Students | bar: Timing Aug to Timing Nov
8 | SEPTEMBER WEEKEND - Presentation to Parents; Review Applications | Chair --> Parents/Students | bar: Timing Sep
9 | OCTOBER WEEKEND - Q&A; Review Applications (Parent Session if Needed). Work with Weekend Chair to plan for December Interview Room Plan. | Chair --> Students | bar: Timing Oct
10 | NOVEMBER WEEKEND - Q&A; Review Applications | Chair --> Students | bar: Timing Nov
11 | Prep for December Interview Day (see prep list) | Chair --> Interviewers/ROTEX | bar: Timing Nov
12 | DECEMBER INTERVIEW DAY (no overnight) | Chair --> Attendees | bar: Timing Dec
13 | Get List of Assigned Countries / Get Mini Flags for January Weekend Presentation | Chair (Flag Lady Store) | bar: Timing Jan
14 | Notify Students of Acceptance (or not) into the Program | Chair --> Students | bar: Timing Jan
15 | JANUARY WEEKEND - Surprise students with country matches (inbounds to help) | Chair --> Inbounds | bar: Timing Jan
16 | JANUARY WEEKEND - Confirm student attendance at Feb Weekend; give info to Weekend Chair / Westerville RC to make Chilly Open Badges. Invite parents to attend Chilly Open. Ask Weekend Chair to arrange for training room at Zoo. | Chair --> Students | bar: Timing Jan
17 | FEBRUARY WEEKEND - no overnight. Students help with tear down at end of event. | Chair --> Students | bar: Timing Feb
18 | Research paper #1 Due | Chair --> Students | bar: Timing Feb
19 | MARCH WEEKEND - no overnight. Meeting with Travel Agent. Blazer Sizing; Head Shots. | Chair --> Attendees | bar: Timing Mar
20 | Order Business Cards - Vista Print | Chair --> Vista Print | Timing Mar: (Distribute cards at Otterbein Weekend.)
21 | Research paper #2 Due | Chair --> Students | bar: Timing Mar
22 | APRIL WEEKEND | Chair --> Students | bar: Timing Apr
23 | Research paper #3 Due | Chair --> Students | bar: Timing Apr
24 | MAY WEEKEND - final weekend. Sign flags and shirts, final goodbyes, etc. | Chair --> Students | bar: Timing May
25 | Research paper #4 Due | Chair --> Students | bar: Timing May
26 | JUNE - Committee Planning Meeting (no student weekend) | Committee | bar: Timing Jun
27 | JULY - Otterbein Weekend for Outbounds. Distribute RYE Business Cards. | Ohio - Erie | bar: Timing Jul
28 | (AUGUST - PROCESS STARTS AGAIN) | bar: Timing Aug
Each RYE Weekend students will participate in training.
- RYE Six Be's, 4 D's, escalation, reports, etc.
Promotion & Prep Stage